## Detailed view
| Saturday |  |  |  | Sunday |  |  |  | Monday |  |  |  | Tuesday |  |  |  | Wednesday |  |  |  | Thursday |  |  |  | Friday
| 2021-10-16 |  |  |  | 2021-10-17 |  |  |  | 2021-10-18 |  |  |  | 2021-10-19 |  |  |  | 2021-10-20 |  |  |  | 2021-10-21 |  |  |  | 2021-10-22
| EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST
Testing Phase | [8 empty] | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity
Schedule | [24 empty] | T2 Release Day schedule
Release deployment and testing
ORT
Migration testing
Service Request and Operational Activity
Special testing
Reporting
Meeting | [24 empty] | MTRSG call
colour legend |  |  |  | New/Updated |  |  |  | Pending agreement
| Saturday |  |  |  | Sunday |  |  |  | Monday |  |  |  | Tuesday |  |  |  | Wednesday |  |  |  | Thursday |  |  |  | Friday
| 2021-10-23 |  |  |  | 2021-10-24 |  |  |  | 2021-10-25 |  |  |  | 2021-10-26 |  |  |  | 2021-10-27 |  |  |  | 2021-10-28 |  |  |  | 2021-10-29
| EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST
Testing Phase | [8 empty] | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity
Schedule | [24 empty] | T2 Release Day schedule
Release deployment and testing
ORT
Migration testing
Service Request and Operational Activity
Special testing |  |  |  | CSLD Business Continuity tests No impact on the tests on Friday and Monday |  |  |  | CSLD Business Continuity tests No impact on the tests on Friday and Monday
Reporting | [24 empty] | Cut-off for reporting for October monthly dashboard
Meeting | [24 empty] | MTRSG call
colour legend |  |  |  | New/Updated |  |  |  | Pending agreement
| Saturday |  |  |  | Sunday |  |  |  | Monday |  |  |  | Tuesday |  |  |  | Wednesday |  |  |  | Thursday |  |  |  | Friday
| 2021-10-30 |  |  |  | 2021-10-31 |  |  |  | 2021-11-01 |  |  |  | 2021-11-02 |  |  |  | 2021-11-03 |  |  |  | 2021-11-04 |  |  |  | 2021-11-05
| EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST
Testing Phase | [8 empty] | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity
Schedule | [24 empty] | T2 Release Day schedule
Release deployment and testing
ORT
Migration testing
Service Request and Operational Activity
Special testing
Reporting | [20 empty] | October month Dashboard submission to MTRSG
Meeting | [16 empty] | 18. MTRSG meeting (CSLD) | [7 empty] | MTRSG call
colour legend |  |  |  | New/Updated |  |  |  | Pending agreement
| Saturday |  |  |  | Sunday |  |  |  | Monday |  |  |  | Tuesday |  |  |  | Wednesday |  |  |  | Thursday |  |  |  | Friday
| 2021-11-06 |  |  |  | 2021-11-07 |  |  |  | 2021-11-08 |  |  |  | 2021-11-09 |  |  |  | 2021-11-10 |  |  |  | 2021-11-11 |  |  |  | 2021-11-12
| EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST
Testing Phase | [8 empty] | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity
Schedule | [24 empty] | T2 Release Day schedule
Release deployment and testing
ORT
Migration testing
Service Request and Operational Activity
Special testing
Reporting
Meeting | [8 empty] | MTRSG meeting/call | [15 empty] | MTRSG call
colour legend |  |  |  | New/Updated |  |  |  | Pending agreement
| Saturday |  |  |  | Sunday |  |  |  | Monday |  |  |  | Tuesday |  |  |  | Wednesday |  |  |  | Thursday |  |  |  | Friday
| 2021-11-13 |  |  |  | 2021-11-14 |  |  |  | 2021-11-15 |  |  |  | 2021-11-16 |  |  |  | 2021-11-17 |  |  |  | 2021-11-18 |  |  |  | 2021-11-19
| EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST
Testing Phase | [8 empty] | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity
Schedule | [24 empty] | T2 Release Day schedule
Release deployment and testing
ORT
Migration testing
Service Request and Operational Activity
Special testing
Reporting
Meeting | [24 empty] | MTRSG call
colour legend |  |  |  | New/Updated |  |  |  | Pending agreement
| Saturday |  |  |  | Sunday |  |  |  | Monday |  |  |  | Tuesday |  |  |  | Wednesday |  |  |  | Thursday |  |  |  | Friday
| 2021-11-20 |  |  |  | 2021-11-21 |  |  |  | 2021-11-22 |  |  |  | 2021-11-23 |  |  |  | 2021-11-24 |  |  |  | 2021-11-25 |  |  |  | 2021-11-26
| EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST
Testing Phase | [8 empty] | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity
Schedule | [12 empty] | T2 closing day due to migration testing |  |  |  | T2 closing day due to migration testing |  |  |  | T2 closing day due to migration testing |  |  |  | T2 Release Day schedule T2 closing day due to migration testing
Release deployment and testing | [8 empty] | MBT tool deployment | [15 empty] | Deployment of SWP3.2 |  |  | Deployment of SWP1, SWP2.3, SWP 2.4, SWP 3.1 and SWP3.2
ORT
Migration testing | [24 empty] | CBT Migration Weekend Rehearsal with Business Date Wednesday 01/12
Service Request and Operational Activity
Special testing
Reporting
Meeting | [24 empty] | MTRSG call
colour legend |  |  |  | New/Updated |  |  |  | Pending agreement
| Saturday |  |  |  | Sunday |  |  |  | Monday |  |  |  | Tuesday |  |  |  | Wednesday |  |  |  | Thursday |  |  |  | Friday
| 2021-11-27 |  |  |  | 2021-11-28 |  |  |  | 2021-11-29 |  |  |  | 2021-11-30 |  |  |  | 2021-12-01 |  |  |  | 2021-12-02 |  |  |  | 2021-12-03
| EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST
Testing Phase | [8 empty] | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity | CBT Mandatory test cases execution CBT 4. Phase Interoperability Migration and Operational Testing |  |  | UT Connectivity | CBT 4. Phase Interoperability Migration and Operational Testing |  |  |  | CBT 4. Phase Interoperability Migration and Operational Testing |  |  |  | CBT 4. Phase Interoperability Migration and Operational Testing
Schedule | T2 closing day due to migration testing |  |  |  | T2 closing day due to migration testing |  |  |  | T2 closing day due to migration testing |  |  |  | T2 closing day due to migration testing | [11 empty] | T2 Release Day schedule
Release deployment and testing
ORT
Migration testing | CBT Migration Weekend Rehearsal with Business Date Wednesday 01/12 |  |  |  | CBT Migration Weekend Rehearsal with Business Date Wednesday 01/12 |  |  |  | CBT Migration Weekend Rehearsal with Business Date Wednesday 01/12 |  |  |  | CBT Migration Weekend Rehearsal with Business Date Wednesday 01/12 | [6 empty] | UT reference data set-up start |  |  |  | UT reference data set-up start |  |  |  | UT reference data set-up start
Service Request and Operational Activity
Special testing
Reporting | [12 empty] | Cut-off for reporting for November monthly dashboard | [11 empty] | November month Dashboard submission to MTRSG
Meeting | [24 empty] | MTRSG call
colour legend |  |  |  | New/Updated |  |  |  | Pending agreement
| Saturday |  |  |  | Sunday |  |  |  | Monday |  |  |  | Tuesday |  |  |  | Wednesday |  |  |  | Thursday |  |  |  | Friday
| 2021-12-04 |  |  |  | 2021-12-05 |  |  |  | 2021-12-06 |  |  |  | 2021-12-07 |  |  |  | 2021-12-08 |  |  |  | 2021-12-09 |  |  |  | 2021-12-10
| EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST | EAC | MIG1 | MIG2 | UTEST
Testing Phase | [8 empty] | CBT 4. Phase Interoperability Migration and Operational Testing |  |  |  | CBT 4. Phase Interoperability Migration and Operational Testing |  |  |  | CBT 4. Phase Interoperability Migration and Operational Testing |  |  |  | CBT 4. Phase Interoperability Migration and Operational Testing |  |  |  | CBT 4. Phase Interoperability Migration and Operational Testing
Schedule | [24 empty] | T2 Release Day schedule
Release deployment and testing
ORT
Migration testing | [11 empty] | UT reference data set-up start |  |  |  | UT reference data set-up start |  |  |  | UT reference data set-up start |  |  |  | UT reference data set-up start |  |  |  | UT reference data set-up start
Service Request and Operational Activity
Special testing
Reporting
Meeting | [8 empty] | MTRSG meeting/call | [15 empty] | MTRSG call
colour legend |  |  |  | New/Updated |  |  |  | Pending agreement
| Saturday |  |  |  | Sunday |  |  |  | Monday |  |  |  | Tuesday |  |  |  | Wednesday |  |  |  | Thursday |  |  |  | Friday
| 2021-12-11 |  |  |  | 2021-12-12 |  |  |  | 2021-12-13 |  |  |  | 2021-12-14 |  |  |  | 2021-12-15 |  |  |  | 2021-12-16 |  |  |  | 2021-12-17
Testing Phase
Schedule
Release deployment and testing
ORT
Migration testing
Service Request and Operational Activity
Special testing
Reporting
Meeting
colour legend |  |  |  | New/Updated |  |  |  | Pending agreement
Formulas:
Sunday = [Saturday]+1
Monday = [Sunday]+1
Tuesday = [Monday]+1
Wednesday = [Tuesday]+1
Thursday = [Wednesday]+1
Friday = [Thursday]+1

## CBT-UT Calendar
Line | Week number | Day/ Week/ Weekend | Start Date | End Date | Activity type | Activities | Pending agreement | EAC | MIG1 | UTEST | future Migrations | W4 | FW | Comments
2 | 43 | Week | 2021-10-18 | 2021-10-22 | Testing stage | CBT Mandatory test cases execution |  | E
3 | 43 | Week | 2021-10-18 | 2021-10-22 | Testing stage | UT Connectivity |  |  |  | U
4 | 43 | Week | 2021-10-18 | 2021-10-22 | Testing stage | CBT 4. Phase Interoperability Migration and Operational Testing |  | E
5 | 43 | Day | 2021-10-22 | 2021-10-22 | Meeting | MTRSG call |  | E
6 | 43 | Day | 2021-10-22 | 2021-10-22 | Schedule | T2 Release Day schedule |  | E
7 | 43 | Weekend | 2021-10-23 | 2021-10-24 | Special testing | CSLD Business Continuity tests |  |  |  | U |  |  |  | No impact on the tests on Friday and Monday
8 | 44 | Week | 2021-10-25 | 2021-10-29 | Testing stage | CBT Mandatory test cases execution |  | E
9 | 44 | Week | 2021-10-25 | 2021-10-29 | Testing stage | UT Connectivity |  |  |  | U
10 | 44 | Week | 2021-10-25 | 2021-10-29 | Testing stage | CBT 4. Phase Interoperability Migration and Operational Testing |  | E
11 | 44 | Day | 2021-10-29 | 2021-10-29 | Meeting | MTRSG call |  | E
12 | 44 | Day | 2021-10-29 | 2021-10-29 | Schedule | T2 Release Day schedule |  | E
13 | 44 | Day | 2021-10-29 | 2021-10-29 | Reporting | Cut-off for reporting for October monthly dashboard |  | E
14 | 45 | Week | 2021-11-01 | 2021-11-05 | Testing stage | CBT Mandatory test cases execution |  | E
15 | 45 | Week | 2021-11-01 | 2021-11-05 | Testing stage | UT Connectivity |  |  |  | U
16 | 45 | Week | 2021-11-01 | 2021-11-05 | Testing stage | CBT 4. Phase Interoperability Migration and Operational Testing |  | E
17 | 45 | Day | 2021-11-03 | 2021-11-03 | Meeting | 18. MTRSG meeting (CSLD) |  | E
18 | 45 | Day | 2021-11-04 | 2021-11-04 | Reporting | October month Dashboard submission to MTRSG |  | E
19 | 45 | Day | 2021-11-05 | 2021-11-05 | Meeting | MTRSG call |  | E
20 | 45 | Day | 2021-11-05 | 2021-11-05 | Schedule | T2 Release Day schedule |  | E
21 | 46 | Day | 2021-11-08 | 2021-11-08 | Meeting | MTRSG meeting/call |  | E
22 | 46 | Week | 2021-11-08 | 2021-11-12 | Testing stage | CBT Mandatory test cases execution |  | E
23 | 46 | Week | 2021-11-08 | 2021-11-12 | Testing stage | UT Connectivity |  |  |  | U
24 | 46 | Week | 2021-11-08 | 2021-11-12 | Testing stage | CBT 4. Phase Interoperability Migration and Operational Testing |  | E
25 | 46 | Day | 2021-11-12 | 2021-11-12 | Meeting | MTRSG call |  | E
26 | 46 | Day | 2021-11-12 | 2021-11-12 | Schedule | T2 Release Day schedule |  | E
27 | 47 | Week | 2021-11-15 | 2021-11-19 | Testing stage | CBT Mandatory test cases execution |  | E
28 | 47 | Week | 2021-11-15 | 2021-11-19 | Testing stage | UT Connectivity |  |  |  | U
29 | 47 | Week | 2021-11-15 | 2021-11-19 | Testing stage | CBT 4. Phase Interoperability Migration and Operational Testing |  | E
30 | 47 | Day | 2021-11-19 | 2021-11-19 | Meeting | MTRSG call |  | E
31 | 47 | Day | 2021-11-19 | 2021-11-19 | Schedule | T2 Release Day schedule |  | E
32 | 48 | Day | 2021-11-22 | 2021-11-22 | Release deployment | MBT tool deployment |  | E
33 | 48 | Week | 2021-11-22 | 2021-11-26 | Testing stage | CBT Mandatory test cases execution |  | E
34 | 48 | Week | 2021-11-22 | 2021-11-26 | Testing stage | UT Connectivity |  |  |  | U
35 | 48 | Week | 2021-11-22 | 2021-11-26 | Testing stage | CBT 4. Phase Interoperability Migration and Operational Testing |  | E
36 | 48 | Day | 2021-11-23 | 2021-11-30 | Schedule | T2 closing day due to migration testing |  | E
37 | 48 | Day | 2021-11-26 | 2021-11-26 | Meeting | MTRSG call |  | E
38 | 48 | Day | 2021-11-26 | 2021-11-26 | Schedule | T2 Release Day schedule |  | E
39 | 48 | Day | 2021-11-26 | 2021-11-26 | Release deployment | Deployment of SWP3.2 |  | E
40 | 48 | Day | 2021-11-26 | 2021-11-26 | Release deployment | Deployment of SWP1, SWP2.3, SWP 2.4, SWP 3.1 and SWP3.2 |  |  |  | U
41 | 48 | Week | 2021-11-26 | 2021-11-30 | Migration testing | CBT Migration Weekend Rehearsal with Business Date Wednesday 01/12 |  | E
42 | 49 | Week | 2021-11-29 | 2021-12-03 | Testing stage | CBT Mandatory test cases execution |  | E
43 | 49 | Week | 2021-11-29 | 2021-12-03 | Testing stage | UT Connectivity |  |  |  | U
44 | 49 | Week | 2021-11-29 | 2021-12-03 | Testing stage | CBT 4. Phase Interoperability Migration and Operational Testing |  | E
45 | 49 | Day | 2021-11-30 | 2021-11-30 | Reporting | Cut-off for reporting for November monthly dashboard |  | E
46 | 49 | Week | 2021-12-01 | 2021-12-03 | Migration testing | UT reference data set-up start |  |  |  | U
47 | 49 | Day | 2021-12-03 | 2021-12-03 | Meeting | MTRSG call |  | E
48 | 49 | Day | 2021-12-03 | 2021-12-03 | Schedule | T2 Release Day schedule |  | E
49 | 49 | Day | 2021-12-03 | 2021-12-03 | Reporting | November month Dashboard submission to MTRSG |  | E
50 | 50 | Day | 2021-12-06 | 2021-12-06 | Meeting | MTRSG meeting/call |  | E
51 | 50 | Week | 2021-12-06 | 2021-12-10 | Testing stage | CBT 4. Phase Interoperability Migration and Operational Testing |  | E
52 | 50 | Week | 2021-12-06 | 2021-12-10 | Migration testing | UT reference data set-up start |  |  |  | U
53 | 50 | Day | 2021-12-10 | 2021-12-10 | Meeting | MTRSG call |  | E
54 | 50 | Day | 2021-12-10 | 2021-12-10 | Schedule | T2 Release Day schedule |  | E
55 | 51 | Week | 2021-12-13 | 2021-12-17 | Testing stage | CBT 4. Phase Interoperability Migration and Operational Testing |  | E
56 | 51 | Week | 2021-12-13 | 2021-12-17 | Migration testing | UT reference data set-up start |  |  |  | U
57 | 51 | Day | 2021-12-15 | 2021-12-15 | Meeting | 19. MTRSG meeting (CSLD) |  | E
58 | 51 | Day | 2021-12-17 | 2021-12-17 | Meeting | MTRSG call |  | E
59 | 51 | Day | 2021-12-17 | 2021-12-17 | Schedule | T2 Release Day schedule |  | E
60 | 52 | Week | 2021-12-20 | 2021-12-24 | Testing stage | CBT 4. Phase Interoperability Migration and Operational Testing |  | E
61 | 52 | Week | 2021-12-20 | 2021-12-24 | Migration testing | UT reference data set-up start |  |  |  | U
62 | 52 | Day | 2021-12-24 | 2021-12-24 | Meeting | MTRSG call |  | E
63 | 52 | Day | 2021-12-24 | 2021-12-24 | Schedule | T2 Release Day schedule |  | E
64 | 52 | Day | 2021-12-24 | 2021-12-24 | Schedule | T2 Closing Day |  | E |  | U
65 | 53 | Week | 2021-12-27 | 2021-12-31 | Testing stage | CBT 4. Phase Interoperability Migration and Operational Testing |  | E
66 | 53 | Week | 2021-12-27 | 2021-12-31 | Migration testing | UT reference data set-up start |  |  |  | U
67 | 53 | Day | 2021-12-31 | 2021-12-31 | Meeting | MTRSG call |  | E
68 | 53 | Day | 2021-12-31 | 2021-12-31 | Schedule | T2 Release Day schedule |  | E
69 | 53 | Day | 2021-12-31 | 2021-12-31 | Schedule | T2 Closing Day |  | E |  | U
70 | 2 | Week | 2022-01-03 | 2022-01-07 | Testing stage | CBT 4. Phase Interoperability Migration and Operational Testing |  | E
71 | 2 | Week | 2022-01-03 | 2022-01-07 | Migration testing | UT reference data set-up start |  |  |  | U
72 | 3 | Week | 2022-01-10 | 2022-01-14 | Testing stage | CBT 4. Phase Interoperability Migration and Operational Testing |  | E
73 | 3 | Week | 2022-01-10 | 2022-01-14 | Migration testing | UT reference data set-up start |  |  |  | U
74 | 4 | Week | 2022-01-17 | 2022-01-21 | Testing stage | CBT 4. Phase Interoperability Migration and Operational Testing |  | E
75 | 4 | Week | 2022-01-17 | 2022-01-21 | Migration testing | UT reference data set-up start |  |  |  | U
76 | 5 | Week | 2022-01-24 | 2022-01-28 | Testing stage | CBT 4. Phase Interoperability Migration and Operational Testing |  | E
77 | 5 | Week | 2022-01-24 | 2022-01-28 | Migration testing | UT reference data set-up start |  |  |  | U
78 | 6 | Week | 2022-01-31 | 2022-02-04 | Testing stage | CBT 4. Phase Interoperability Migration and Operational Testing |  | E
79 | 6 | Week | 2022-01-31 | 2022-02-04 | Migration testing | UT reference data set-up start |  |  |  | U
80 | 6 | Day | 2022-02-02 | 2022-02-04 | Migration testing | CBT MWR |  | E
81 | 6 | Day | 2022-02-04 | 2022-02-04 | Migration testing | Connection of T2S to T2 |  | E
82 | 7 | Week | 2022-02-07 | 2022-02-11 | Testing stage | CBT 4. Phase Interoperability Migration and Operational Testing |  | E
83 | 7 | Week | 2022-02-07 | 2022-02-11 | Migration testing | UT reference data set-up start |  |  |  | U
84 | 8 | Week | 2022-02-14 | 2022-02-18 | Testing stage | CBT 4. Phase Interoperability Migration and Operational Testing |  | E
85 | 8 | Week | 2022-02-14 | 2022-02-18 | Migration testing | UT reference data set-up start |  |  |  | U
86 | 9 | Week | 2022-02-21 | 2022-02-25 | Migration testing | UT reference data set-up start |  |  |  | U
87 | 9 | Week | 2022-02-21 | 2022-02-25 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
88 | 10 | Week | 2022-02-28 | 2022-03-04 | Migration testing | UT reference data set-up start |  |  |  | U
89 | 10 | Week | 2022-02-28 | 2022-03-04 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
90 | 11 | Week | 2022-03-07 | 2022-03-11 | Migration testing | UT reference data set-up start |  |  |  | U
91 | 11 | Week | 2022-03-07 | 2022-03-11 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
92 | 12 | Week | 2022-03-14 | 2022-03-18 | Migration testing | UT reference data set-up start |  |  |  | U
93 | 12 | Week | 2022-03-14 | 2022-03-18 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
94 | 13 | Week | 2022-03-21 | 2022-03-25 | Migration testing | UT reference data set-up start |  |  |  | U
95 | 13 | Week | 2022-03-21 | 2022-03-25 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
96 | 14 | Day | 2022-03-28 | 2022-03-31 | Migration testing | UT MWR |  |  |  | U
97 | 14 | Week | 2022-03-28 | 2022-04-01 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
98 | 14 | Day | 2022-04-01 | 2022-04-01 | Release deployment | Deployment of SWP4.1 |  | E |  | U
99 | 14 | Week | 2022-04-01 | 2022-04-01 | Testing stage | UT Community with Simulators | Y |  |  | U
100 | 14 | Week | 2022-04-01 | 2022-04-01 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
101 | 14 | Week | 2022-04-01 | 2022-04-01 | Testing stage | UT Operational Tests | Y |  |  | U
102 | 15 | Week | 2022-04-04 | 2022-04-08 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
103 | 15 | Week | 2022-04-04 | 2022-04-08 | Testing stage | UT Community with Simulators | Y |  |  | U
104 | 15 | Week | 2022-04-04 | 2022-04-08 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
105 | 15 | Week | 2022-04-04 | 2022-04-08 | Testing stage | UT Operational Tests | Y |  |  | U
106 | 16 | Week | 2022-04-11 | 2022-04-15 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
107 | 16 | Week | 2022-04-11 | 2022-04-15 | Testing stage | UT Community with Simulators | Y |  |  | U
108 | 16 | Week | 2022-04-11 | 2022-04-15 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
109 | 16 | Week | 2022-04-11 | 2022-04-15 | Testing stage | UT Operational Tests | Y |  |  | U
110 | 17 | Week | 2022-04-18 | 2022-04-22 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
111 | 17 | Week | 2022-04-18 | 2022-04-22 | Testing stage | UT Community with Simulators | Y |  |  | U
112 | 17 | Week | 2022-04-18 | 2022-04-22 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
113 | 17 | Week | 2022-04-18 | 2022-04-22 | Testing stage | UT Operational Tests | Y |  |  | U
114 | 17 | Day | 2022-04-22 | 2022-04-22 | Release deployment | Deployment of SWP4.2 |  | E |  | U
115 | 18 | Week | 2022-04-25 | 2022-04-29 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
116 | 18 | Week | 2022-04-25 | 2022-04-29 | Testing stage | UT Community with Simulators | Y |  |  | U
117 | 18 | Week | 2022-04-25 | 2022-04-29 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
118 | 18 | Week | 2022-04-25 | 2022-04-29 | Testing stage | UT Operational Tests | Y |  |  | U
119 | 19 | Week | 2022-05-02 | 2022-05-06 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
120 | 19 | Week | 2022-05-02 | 2022-05-06 | Testing stage | UT Community with Simulators | Y |  |  | U
121 | 19 | Week | 2022-05-02 | 2022-05-06 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
122 | 19 | Week | 2022-05-02 | 2022-05-06 | Testing stage | UT Operational Tests | Y |  |  | U
123 | 20 | Week | 2022-05-09 | 2022-05-13 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
124 | 20 | Week | 2022-05-09 | 2022-05-13 | Testing stage | UT Community with Simulators | Y |  |  | U
125 | 20 | Week | 2022-05-09 | 2022-05-13 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
126 | 20 | Week | 2022-05-09 | 2022-05-13 | Testing stage | UT Operational Tests | Y |  |  | U
127 | 21 | Week | 2022-05-16 | 2022-05-20 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
128 | 21 | Week | 2022-05-16 | 2022-05-20 | Testing stage | UT Community with Simulators | Y |  |  | U
129 | 21 | Week | 2022-05-16 | 2022-05-20 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
130 | 21 | Week | 2022-05-16 | 2022-05-20 | Testing stage | UT Operational Tests | Y |  |  | U
131 | 22 | Week | 2022-05-23 | 2022-05-27 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
132 | 22 | Week | 2022-05-23 | 2022-05-27 | Testing stage | UT Community with Simulators | Y |  |  | U
133 | 22 | Week | 2022-05-23 | 2022-05-27 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
134 | 22 | Week | 2022-05-23 | 2022-05-27 | Testing stage | UT Operational Tests | Y |  |  | U
135 | 23 | Week | 2022-05-30 | 2022-06-03 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
136 | 23 | Week | 2022-05-30 | 2022-06-03 | Testing stage | UT Community with Simulators | Y |  |  | U
137 | 23 | Week | 2022-05-30 | 2022-06-03 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
138 | 23 | Week | 2022-05-30 | 2022-06-03 | Testing stage | UT Operational Tests | Y |  |  | U
139 | 24 | Week | 2022-06-06 | 2022-06-10 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
140 | 24 | Week | 2022-06-06 | 2022-06-10 | Testing stage | UT Community with Simulators | Y |  |  | U
141 | 24 | Week | 2022-06-06 | 2022-06-10 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
142 | 24 | Week | 2022-06-06 | 2022-06-10 | Testing stage | UT Operational Tests | Y |  |  | U
143 | 25 | Week | 2022-06-13 | 2022-06-17 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
144 | 25 | Week | 2022-06-13 | 2022-06-17 | Testing stage | UT Community with Simulators | Y |  |  | U
145 | 25 | Week | 2022-06-13 | 2022-06-17 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
146 | 25 | Week | 2022-06-13 | 2022-06-17 | Testing stage | UT Operational Tests | Y |  |  | U
147 | 26 | Week | 2022-06-20 | 2022-06-24 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
148 | 26 | Week | 2022-06-20 | 2022-06-24 | Testing stage | UT Community with Simulators | Y |  |  | U
149 | 26 | Week | 2022-06-20 | 2022-06-24 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
150 | 26 | Week | 2022-06-20 | 2022-06-24 | Testing stage | UT Operational Tests | Y |  |  | U
151 | 27 | Week | 2022-06-27 | 2022-07-01 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
152 | 27 | Week | 2022-06-27 | 2022-07-01 | Testing stage | UT Community with Simulators | Y |  |  | U
153 | 27 | Week | 2022-06-27 | 2022-07-01 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
154 | 27 | Week | 2022-06-27 | 2022-07-01 | Testing stage | UT Operational Tests | Y |  |  | U
155 | 28 | Week | 2022-07-04 | 2022-07-08 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
156 | 28 | Week | 2022-07-04 | 2022-07-08 | Testing stage | UT Community with Simulators | Y |  |  | U
157 | 28 | Week | 2022-07-04 | 2022-07-08 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
158 | 28 | Week | 2022-07-04 | 2022-07-08 | Testing stage | UT Operational Tests | Y |  |  | U
159 | 28 | Weekend | 2022-07-08 | 2022-07-10 | Migration testing | TIPS connection to T2 |  | E
160 | 28 | Weekend | 2022-07-08 | 2022-07-10 | Migration testing | CSLD UT MWDR and T2S & TIPS connection to T2 |  |  |  | U
161 | 29 | Week | 2022-07-11 | 2022-07-15 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
162 | 29 | Week | 2022-07-11 | 2022-07-15 | Testing stage | UT Community with Simulators | Y |  |  | U
163 | 29 | Week | 2022-07-11 | 2022-07-15 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
164 | 29 | Week | 2022-07-11 | 2022-07-15 | Testing stage | UT Operational Tests | Y |  |  | U
165 | 30 | Week | 2022-07-18 | 2022-07-22 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
166 | 30 | Week | 2022-07-18 | 2022-07-22 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
167 | 30 | Week | 2022-07-18 | 2022-07-22 | Testing stage | UT Operational Tests | Y |  |  | U
168 | 30 | Week | 2022-07-18 | 2022-07-22 | Testing stage | UT Business Day with T2S and TIPS |  |  |  | U
169 | 31 | Week | 2022-07-25 | 2022-07-29 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
170 | 31 | Week | 2022-07-25 | 2022-07-29 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
171 | 31 | Week | 2022-07-25 | 2022-07-29 | Testing stage | UT Operational Tests | Y |  |  | U
172 | 31 | Week | 2022-07-25 | 2022-07-29 | Testing stage | UT Business Day with T2S and TIPS |  |  |  | U
173 | 32 | Week | 2022-08-01 | 2022-08-05 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
174 | 32 | Week | 2022-08-01 | 2022-08-05 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
175 | 32 | Week | 2022-08-01 | 2022-08-05 | Testing stage | UT Operational Tests | Y |  |  | U
176 | 32 | Week | 2022-08-01 | 2022-08-05 | Testing stage | UT Business Day with T2S and TIPS |  |  |  | U
177 | 33 | Week | 2022-08-08 | 2022-08-12 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
178 | 33 | Week | 2022-08-08 | 2022-08-12 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
179 | 33 | Week | 2022-08-08 | 2022-08-12 | Testing stage | UT Operational Tests | Y |  |  | U
180 | 33 | Week | 2022-08-08 | 2022-08-12 | Testing stage | UT Business Day with T2S and TIPS |  |  |  | U
181 | 33 | Weekend | 2022-08-10 | 2022-08-11 | Migration testing | CBT MWDR |  | E
182 | 34 | Week | 2022-08-15 | 2022-08-19 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
183 | 34 | Week | 2022-08-15 | 2022-08-19 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
184 | 34 | Week | 2022-08-15 | 2022-08-19 | Testing stage | UT Operational Tests | Y |  |  | U
185 | 34 | Week | 2022-08-15 | 2022-08-19 | Testing stage | UT Business Day with T2S and TIPS |  |  |  | U
186 | 35 | Week | 2022-08-22 | 2022-08-26 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
187 | 35 | Week | 2022-08-22 | 2022-08-26 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
188 | 35 | Week | 2022-08-22 | 2022-08-26 | Testing stage | UT Operational Tests | Y |  |  | U
189 | 35 | Week | 2022-08-22 | 2022-08-26 | Testing stage | UT Business Day with T2S and TIPS |  |  |  | U
190 | 36 | Week | 2022-08-29 | 2022-09-02 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
191 | 36 | Week | 2022-08-29 | 2022-09-02 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
192 | 36 | Week | 2022-08-29 | 2022-09-02 | Testing stage | UT Operational Tests | Y |  |  | U
193 | 36 | Week | 2022-08-29 | 2022-09-02 | Testing stage | UT Business Day with T2S and TIPS |  |  |  | U
194 | 37 | Week | 2022-09-05 | 2022-09-09 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
195 | 37 | Week | 2022-09-05 | 2022-09-09 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
196 | 37 | Week | 2022-09-05 | 2022-09-09 | Testing stage | UT Operational Tests | Y |  |  | U
197 | 37 | Week | 2022-09-05 | 2022-09-09 | Testing stage | UT Business Day with T2S and TIPS |  |  |  | U
198 | 38 | Week | 2022-09-12 | 2022-09-16 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
199 | 38 | Week | 2022-09-12 | 2022-09-16 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
200 | 38 | Week | 2022-09-12 | 2022-09-16 | Testing stage | UT Operational Tests | Y |  |  | U
201 | 38 | Week | 2022-09-12 | 2022-09-16 | Testing stage | UT Business Day with T2S and TIPS |  |  |  | U
202 | 39 | Week | 2022-09-19 | 2022-09-23 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
203 | 39 | Week | 2022-09-19 | 2022-09-23 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
204 | 39 | Week | 2022-09-19 | 2022-09-23 | Testing stage | UT Operational Tests | Y |  |  | U
205 | 39 | Week | 2022-09-19 | 2022-09-23 | Testing stage | UT Business Day with T2S and TIPS |  |  |  | U
206 | 39 | Weekend | 2022-09-23 | 2022-09-24 | Migration testing | UT MWDR |  |  |  | U
207 | 40 | Week | 2022-09-26 | 2022-09-30 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
208 | 40 | Week | 2022-09-26 | 2022-09-30 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
209 | 40 | Week | 2022-09-26 | 2022-09-30 | Testing stage | UT Operational Tests | Y |  |  | U
210 | 40 | Week | 2022-09-26 | 2022-09-30 | Testing stage | UT Business Day with T2S and TIPS |  |  |  | U
211 | 41 | Week | 2022-10-03 | 2022-10-07 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
212 | 41 | Week | 2022-10-03 | 2022-10-07 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
213 | 41 | Week | 2022-10-03 | 2022-10-07 | Testing stage | UT Operational Tests | Y |  |  | U
214 | 41 | Week | 2022-10-03 | 2022-10-07 | Testing stage | UT Business Day with T2S and TIPS |  |  |  | U
215 | 42 | Week | 2022-10-10 | 2022-10-14 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
216 | 42 | Week | 2022-10-10 | 2022-10-14 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
217 | 42 | Week | 2022-10-10 | 2022-10-14 | Testing stage | UT Operational Tests | Y |  |  | U
218 | 42 | Week | 2022-10-10 | 2022-10-14 | Testing stage | UT Business Day with T2S and TIPS |  |  |  | U
219 | 42 | Weekend | 2022-10-15 | 2022-10-16 | Migration testing | UT MWR optional | Y |  |  | U
220 | 43 | Week | 2022-10-17 | 2022-10-21 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
221 | 43 | Week | 2022-10-17 | 2022-10-21 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
222 | 43 | Week | 2022-10-17 | 2022-10-21 | Testing stage | UT Operational Tests | Y |  |  | U
223 | 43 | Week | 2022-10-17 | 2022-10-21 | Testing stage | UT Business Day with T2S and TIPS |  |  |  | U
224 | 44 | Week | 2022-10-24 | 2022-10-28 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
225 | 44 | Week | 2022-10-24 | 2022-10-28 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
226 | 44 | Week | 2022-10-24 | 2022-10-28 | Testing stage | UT Operational Tests | Y |  |  | U
227 | 44 | Week | 2022-10-24 | 2022-10-28 | Testing stage | UT Business Day with T2S and TIPS |  |  |  | U
228 | 45 | Week | 2022-10-31 | 2022-11-04 | Testing stage | CBT 5. Phase Interoperability, Operational Testing and Migration testing |  | E
229 | 45 | Week | 2022-10-31 | 2022-11-04 | Testing stage | UT Mandatory test cases execution | Y |  |  | U
230 | 45 | Week | 2022-10-31 | 2022-11-04 | Testing stage | UT Operational Tests | Y |  |  | U
Formulas:
Week number = WEEKNUM([Start Date])