## Cal_ext_ECB_unrestricted
Week number | Day/ Week/ Weekend | Start Date | End Date | Activity type | Activities | Comments
5 | Week | 2025-01-27 | 2025-01-29 | Schedule | T2 Live Timing | To support ECMS testing campaign
5 | Day | 2025-01-29 | 2025-01-29 | Special testing | Open ECONSII from 10:00 - 12:00 CET
5 | Day | 2025-01-29 | 2025-01-29 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
5 | Day | 2025-01-29 | 2025-01-29 | ORT | T2S ORT "Delay in start of DVP cut-off (EUR)" with impact on T2 | Impact on T2: depending on exact test scenario chosen there will be a delayed closing of CLM and RTGS; EoD and SoD events postponed
5 | Day | 2025-01-29 | 2025-01-29 | Special testing | BILL invoice for NCBs | Billing period 20/01/-26/01/2025
5 | Day | 2025-01-30 | 2025-01-30 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
5 | Day | 2025-01-30 | 2025-01-30 | Schedule | T2 closing day for DKK settlement; Live timing for EUR settlement | To support testing T2 HF PBI234106 (DKK) & ECMS testing campaign (EUR)
5 | Day | 2025-01-31 | 2025-01-31 | Schedule | T2 closing day for EUR settlement; Release day for DKK settlement | To support ECMS testing campaign
6 | Week | 2025-02-03 | 2025-02-05 | Schedule | T2 Live Timing | To support ECMS testing campaign
6 | Day | 2025-02-05 | 2025-02-05 | Special testing | Open ECONSII from 10:00 - 12:00 CET
6 | Day | 2025-02-05 | 2025-02-05 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
6 | Day | 2025-02-05 | 2025-02-05 | Special testing | BILL invoice for NCBs | Billing period 27/01/-31/01/2025
6 | Day | 2025-02-06 | 2025-02-06 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
6 | Day | 2025-02-06 | 2025-02-06 | Schedule | T2 closing day for DKK settlement; Live timing for EUR settlement | To support testing T2 HF PBI234106 (DKK) & ECMS testing campaign (EUR)
6 | Day | 2025-02-07 | 2025-02-07 | Schedule | T2 Synchronised Release day
6 | Day | 2025-02-07 | 2025-02-07 | Operational activity | T2 hot fix deployment (PBI235017) | PROD deployment of HF foreseen on 28/03/2025
7 | Week | 2025-02-10 | 2025-02-13 | Schedule | T2 Synchronised Standard day
7 | Day | 2025-02-12 | 2025-02-12 | Special testing | Open ECONSII from 10:00 - 12:00 CET
7 | Day | 2025-02-12 | 2025-02-12 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
7 | Day | 2025-02-12 | 2025-02-12 | ORT | ECMS ORT "Activation of ECONSII" with impact on T2 | T2-SMSG to organise and communicate details about ORT and involvement of T2 community
7 | Day | 2025-02-13 | 2025-02-13 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
7 | Day | 2025-02-14 | 2025-02-14 | Schedule | T2 Synchronised Release day
8 | Week | 2025-02-17 | 2025-02-20 | Schedule | T2 Synchronised Standard day
8 | Day | 2025-02-19 | 2025-02-19 | Special testing | Open ECONSII from 10:00 - 12:00 CET
8 | Day | 2025-02-19 | 2025-02-19 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
8 | Day | 2025-02-20 | 2025-02-20 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
8 | Day | 2025-02-21 | 2025-02-21 | Schedule | T2 Synchronised Release day
8 | Weekend | 2025-02-21 | 2025-02-21 | Migration testing | DKCB - DR3 - MWDR | Activities start after deployment
8 | Weekend | 2025-02-22 | 2025-02-22 | Migration testing | DKCB - DR3 - MWDR | entire community
9 | Week | 2025-02-24 | 2025-02-27 | Schedule | T2 Synchronised Standard day
9 | Day | 2025-02-26 | 2025-02-26 | Special testing | Open ECONSII from 10:00 - 12:00 CET
9 | Day | 2025-02-26 | 2025-02-26 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
9 | Day | 2025-02-27 | 2025-02-27 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
9 | Day | 2025-02-28 | 2025-02-28 | Schedule | T2 Synchronised Release day
10 | Week | 2025-03-03 | 2025-03-06 | Schedule | T2 Live Timing | To support ECMS testing campaign
10 | Day | 2025-03-05 | 2025-03-05 | Special testing | Open ECONSII from 10:00 - 12:00 CET
10 | Day | 2025-03-05 | 2025-03-05 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
10 | Day | 2025-03-05 | 2025-03-05 | Special testing | BILL invoice for NCBs | Billing period 01/02/-28/02/2025
10 | Day | 2025-03-06 | 2025-03-06 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
10 | Day | 2025-03-07 | 2025-03-07 | Schedule | T2 Synchronised Release day
11 | Week | 2025-03-10 | 2025-03-13 | Schedule | T2 Live Timing | To support ECMS testing campaign
11 | Day | 2025-03-12 | 2025-03-12 | Special testing | Open ECONSII from 10:00 - 12:00 CET
11 | Day | 2025-03-12 | 2025-03-12 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
11 | Day | 2025-03-13 | 2025-03-13 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
11 | Day | 2025-03-14 | 2025-03-14 | Schedule | T2 Synchronised Release day
12 | Week | 2025-03-17 | 2025-03-20 | Schedule | T2 Live Timing | To support ECMS testing campaign
12 | Day | 2025-03-19 | 2025-03-19 | Special testing | Open ECONSII from 10:00 - 12:00 CET
12 | Day | 2025-03-19 | 2025-03-19 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
12 | Day | 2025-03-20 | 2025-03-20 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
12 | Day | 2025-03-21 | 2025-03-21 | Schedule | T2 Synchronised Release day
12 | Weekend | 2025-03-21 | 2025-03-21 | Migration testing | DKCB - DR4 - MWDR (optional)
12 | Weekend | 2025-03-22 | 2025-03-22 | Migration testing | DKCB - DR4 - MWDR (optional)
13 | Week | 2025-03-24 | 2025-03-27 | Schedule | T2 Synchronised Standard day
13 | Day | 2025-03-26 | 2025-03-26 | Special testing | Open ECONSII from 10:00 - 12:00 CET
13 | Day | 2025-03-26 | 2025-03-26 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
13 | Day | 2025-03-27 | 2025-03-27 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
13 | Day | 2025-03-28 | 2025-03-28 | Schedule | T2 closing day for EUR settlement; Release day for DKK settlement
13 | Day | 2025-03-28 | 2025-03-28 | ORT | T2S ORT "T2S open during RTGS closing day (EUR)" with impact on T2 | Impact on T2: to support the T2S ORT T2 is closed for EUR settlement
14 | Week | 2025-03-31 | 2025-04-02 | Schedule | T2 Synchronised Standard day
14 | Day | 2025-04-02 | 2025-04-02 | Special testing | Open ECONSII from 10:00 - 12:00 CET
14 | Day | 2025-04-02 | 2025-04-02 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
14 | Day | 2025-04-03 | 2025-04-03 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
14 | Day | 2025-04-03 | 2025-04-03 | Special testing | BILL invoice for NCBs | Billing period 01/03/-31/03/2025
14 | Day | 2025-04-03 | 2025-04-03 | Schedule | T2 Live Timing | To support FRCB contingency tests
14 | Day | 2025-04-04 | 2025-04-04 | Schedule | T2 Live Timing | To support ECMS MWDR
15 | Week | 2025-04-07 | 2025-04-10 | Schedule | T2 Live Timing | To support ECMS testing campaign
15 | Day | 2025-04-09 | 2025-04-09 | Special testing | Open ECONSII from 10:00 - 12:00 CET
15 | Day | 2025-04-09 | 2025-04-09 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
15 | Day | 2025-04-10 | 2025-04-10 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
15 | Day | 2025-04-11 | 2025-04-11 | Schedule | T2 Synchronised Release day
16 | Day | 2025-04-14 | 2025-04-14 | Reporting | Service Transition Status Report (STSR) for T2 R2025.JUN in Pre-Production (cut-off and delivery to T2-WG)
16 | Week | 2025-04-14 | 2025-04-16 | Schedule | T2 Live Timing | To support ECMS testing campaign
16 | Day | 2025-04-15 | 2025-04-15 | Reporting | T2-WG Go / No-go decision to deploy T2 R2025.JUN to Pre-Production | 8 business days before UTEST deployment
16 | Day | 2025-04-16 | 2025-04-16 | Special testing | Open ECONSII from 10:00 - 12:00 CET
16 | Day | 2025-04-16 | 2025-04-16 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
16 | Day | 2025-04-17 | 2025-04-17 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
16 | Day | 2025-04-17 | 2025-04-17 | Schedule | T2 closing day for DKK settlement; Live timing for EUR settlement | Maundy Thursday & live timing to support ECMS testing campaign
16 | Day | 2025-04-18 | 2025-04-18 | Schedule | T2 closing day | Good Friday
17 | Day | 2025-04-21 | 2025-04-21 | Schedule | T2 closing day | Easter Monday
17 | Day | 2025-04-22 | 2025-04-24 | Schedule | T2 Live Timing | To support ECMS testing campaign
17 | Day | 2025-04-23 | 2025-04-23 | Special testing | Open ECONSII from 10:00 - 12:00 CET
17 | Day | 2025-04-23 | 2025-04-23 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
17 | Day | 2025-04-24 | 2025-04-24 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
17 | Day | 2025-04-25 | 2025-04-25 | Schedule | T2 Synchronised Release day
18 | Day | 2025-04-28 | 2025-04-28 | Schedule | T2 Synchronised Release day | to facilitate deployment of R2025.JUN
18 | Day | 2025-04-29 | 2025-04-29 | Release deployment | T2 R2025.JUN deployment to Pre-Production (Packages 1-7) | Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
18 | Day | 2025-04-29 | 2025-04-29 | Schedule | T2 closing day | to facilitate deployment of R2025.JUN
18 | Day | 2025-04-30 | 2025-04-30 | Special testing | Open ECONSII from 10:00 - 12:00 CET
18 | Day | 2025-04-30 | 2025-04-30 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
18 | Day | 2025-04-30 | 2025-04-30 | Release testing | Start of testing of T2 R2025.JUN scope elements in Pre-Production
18 | Day | 2025-04-30 | 2025-04-30 | Schedule | T2 Synchronised Standard day
18 | Week | 2025-04-30 | 2025-05-02 | Release testing | T2 R2025.JUN Release testing in Pre-Production
18 | Day | 2025-05-01 | 2025-05-01 | Schedule | T2 closing day | Labour day / clarification ongoing about opening T2 DKK (pending results of DA for CR T2-0133-SYS)
18 | Day | 2025-05-02 | 2025-05-02 | Schedule | T2 Synchronised Release day
18 | Day | 2025-05-02 | 2025-05-02 | Release deployment | T2 R2025.JUN deployment (Package 8) | RD only / Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
18 | Day | 2025-05-02 | 2025-05-02 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
19 | Week | 2025-05-05 | 2025-05-08 | Schedule | T2 Synchronised Standard day
19 | Week | 2025-05-05 | 2025-05-09 | Release testing | T2 R2025.JUN Release testing in Pre-Production
19 | Day | 2025-05-06 | 2025-05-06 | Special testing | BILL invoice for NCBs | Billing period 01/04/-30/04/2025
19 | Day | 2025-05-07 | 2025-05-07 | Special testing | Open ECONSII from 10:00 - 12:00 CET
19 | Day | 2025-05-07 | 2025-05-07 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
19 | Day | 2025-05-08 | 2025-05-08 | Release deployment | T2 R2025.JUN deployment (Package 9) | critical RD only / Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
19 | Day | 2025-05-08 | 2025-05-08 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
19 | Day | 2025-05-09 | 2025-05-09 | Schedule | T2 Live Timing | To support ECMS MWDR
20 | Week | 2025-05-12 | 2025-05-15 | Schedule | T2 Live Timing
20 | Week | 2025-05-12 | 2025-05-16 | Release testing | T2 R2025.JUN Release testing in Pre-Production
20 | Day | 2025-05-14 | 2025-05-14 | Special testing | Open ECONSII from 10:00 - 12:00 CET
20 | Day | 2025-05-14 | 2025-05-14 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
20 | Day | 2025-05-14 | 2025-05-14 | ORT | T2S ORT "Delay in RTGS start (processing without liquidity) (EUR)" with impact on T2 | Impact on T2: a delay in the start of new business day in CLM and RTGS will be simulated
20 | Day | 2025-05-15 | 2025-05-15 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
20 | Day | 2025-05-16 | 2025-05-16 | Schedule | T2 Synchronised Release day
20 | Day | 2025-05-16 | 2025-05-16 | Release deployment | T2 R2025.JUN deployment (Package 10) | critical RD only / Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
21 | Week | 2025-05-19 | 2025-05-22 | Schedule | T2 Live Timing
21 | Week | 2025-05-19 | 2025-05-23 | Release testing | T2 R2025.JUN Release testing in Pre-Production
21 | Day | 2025-05-21 | 2025-05-21 | Special testing | Open ECONSII from 10:00 - 12:00 CET
21 | Day | 2025-05-21 | 2025-05-21 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
21 | Day | 2025-05-22 | 2025-05-22 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
21 | Day | 2025-05-23 | 2025-05-23 | Schedule | T2 Synchronised Release day
21 | Day | 2025-05-23 | 2025-05-23 | Release deployment | T2 R2025.JUN deployment (Package 11) | critical RD only / Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
22 | Week | 2025-05-26 | 2025-05-27 | Release testing | T2 R2025.JUN Release testing in Pre-Production
22 | Week | 2025-05-26 | 2025-05-28 | Schedule | T2 Synchronised Standard day
22 | Day | 2025-05-27 | 2025-05-27 | Release testing | End of testing of T2 R2025.JUN scope elements in Pre-Production
22 | Day | 2025-05-28 | 2025-05-28 | Special testing | Open ECONSII from 10:00 - 12:00 CET
22 | Day | 2025-05-28 | 2025-05-28 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
22 | Day | 2025-05-29 | 2025-05-29 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
22 | Day | 2025-05-29 | 2025-05-29 | Schedule | T2 closing day for DKK settlement; Standard day for EUR settlement | Ascension Day
22 | Day | 2025-05-30 | 2025-05-30 | Schedule | T2 closing day for DKK settlement; Release day for EUR settlement | Bank Holiday
22 | Day | 2025-05-30 | 2025-05-30 | Release deployment | T2 R2025.JUN deployment (Package 12) | critical RD only / Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
23 | Week | 2025-06-02 | 2025-06-04 | Schedule | T2 Synchronised Standard day
23 | Day | 2025-06-04 | 2025-06-04 | Special testing | Open ECONSII from 10:00 - 12:00 CET
23 | Day | 2025-06-04 | 2025-06-04 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
23 | Day | 2025-06-04 | 2025-06-04 | Special testing | BILL invoice for NCBs | Billing period 01/05/-31/05/2025
23 | Day | 2025-06-05 | 2025-06-05 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
23 | Day | 2025-06-05 | 2025-06-05 | Schedule | T2 closing day for DKK settlement; Standard day for EUR settlement | Bank Holiday (DK Constitution Day)
23 | Day | 2025-06-06 | 2025-06-06 | Schedule | T2 Synchronised Release day
23 | Day | 2025-06-06 | 2025-06-06 | Release deployment | T2 R2025.JUN deployment (Package 13) | critical RD only / Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
24 | Day | 2025-06-09 | 2025-06-09 | Schedule | T2 closing day for DKK settlement; Standard day for EUR settlement | Whit Monday
24 | Day | 2025-06-10 | 2025-06-12 | Schedule | T2 Synchronised Standard day
24 | Day | 2025-06-11 | 2025-06-11 | Special testing | Open ECONSII from 10:00 - 12:00 CET
24 | Day | 2025-06-11 | 2025-06-11 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
24 | Day | 2025-06-12 | 2025-06-12 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
24 | Day | 2025-06-13 | 2025-06-13 | Schedule | T2 Synchronised Release day
25 | Week | 2025-06-16 | 2025-06-19 | Schedule | T2 Synchronised Standard day
25 | Day | 2025-06-18 | 2025-06-18 | Special testing | Open ECONSII from 10:00 - 12:00 CET
25 | Day | 2025-06-18 | 2025-06-18 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
25 | Day | 2025-06-19 | 2025-06-19 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
25 | Day | 2025-06-20 | 2025-06-20 | Schedule | T2 Synchronised Release day
26 | Week | 2025-06-23 | 2025-06-26 | Schedule | T2 Synchronised Standard day
26 | Day | 2025-06-25 | 2025-06-25 | Special testing | Open ECONSII from 10:00 - 12:00 CET
26 | Day | 2025-06-25 | 2025-06-25 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
26 | Day | 2025-06-26 | 2025-06-26 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
26 | Day | 2025-06-26 | 2025-06-26 | ORT | T2 ORT "Rescheduling of events (leading to delayed closing of CLM and RTGS)"
26 | Day | 2025-06-27 | 2025-06-27 | Schedule | T2 Synchronised Release day
27 | Week | 2025-06-30 | 2025-07-03 | Schedule | T2 Synchronised Standard day
27 | Day | 2025-07-02 | 2025-07-02 | Special testing | Open ECONSII from 10:00 - 12:00 CET
27 | Day | 2025-07-02 | 2025-07-02 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
27 | Day | 2025-07-03 | 2025-07-03 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
27 | Day | 2025-07-03 | 2025-07-03 | Special testing | BILL invoice for NCBs | Billing period 01/06/-30/06/2025
27 | Day | 2025-07-04 | 2025-07-04 | Schedule | T2 Synchronised Release day
28 | Week | 2025-07-07 | 2025-07-10 | Schedule | T2 Synchronised Standard day
28 | Day | 2025-07-09 | 2025-07-09 | Special testing | Open ECONSII from 10:00 - 12:00 CET
28 | Day | 2025-07-09 | 2025-07-09 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
28 | Day | 2025-07-10 | 2025-07-10 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
28 | Day | 2025-07-11 | 2025-07-11 | Schedule | T2 Synchronised Release day
29 | Week | 2025-07-14 | 2025-07-17 | Schedule | T2 Synchronised Standard day
29 | Day | 2025-07-16 | 2025-07-16 | Special testing | Open ECONSII from 10:00 - 12:00 CET
29 | Day | 2025-07-16 | 2025-07-16 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
29 | Day | 2025-07-17 | 2025-07-17 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
29 | Day | 2025-07-18 | 2025-07-18 | Schedule | T2 Synchronised Release day
30 | Week | 2025-07-21 | 2025-07-24 | Schedule | T2 Synchronised Standard day
30 | Day | 2025-07-23 | 2025-07-23 | Special testing | Open ECONSII from 10:00 - 12:00 CET
30 | Day | 2025-07-23 | 2025-07-23 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
30 | Day | 2025-07-24 | 2025-07-24 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
30 | Day | 2025-07-25 | 2025-07-25 | Schedule | T2 Synchronised Release day
31 | Week | 2025-07-28 | 2025-07-31 | Schedule | T2 Synchronised Standard day
31 | Day | 2025-07-30 | 2025-07-30 | Special testing | Open ECONSII from 10:00 - 12:00 CET
31 | Day | 2025-07-30 | 2025-07-30 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
31 | Day | 2025-07-31 | 2025-07-31 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
31 | Day | 2025-08-01 | 2025-08-01 | Schedule | T2 Synchronised Release day
32 | Day | 2025-08-04 | 2025-08-05 | Schedule | T2 Synchronised Standard day
32 | Day | 2025-08-05 | 2025-08-05 | Special testing | BILL invoice for NCBs | Billing period 01/07/-31/07/2025
32 | Day | 2025-08-06 | 2025-08-06 | Schedule | T2 closing day for DKK settlement; Standard day for EUR settlement
32 | Day | 2025-08-06 | 2025-08-06 | Special testing | Open ECONSII from 10:00 - 12:00 CET
32 | Day | 2025-08-06 | 2025-08-06 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
32 | Day | 2025-08-06 | 2025-08-06 | ORT | T2S ORT "T2S open during RTGS closing day (DKK)" with impact on T2 | Impact on T2: to support the T2S ORT T2 is closed for DKK settlement
32 | Day | 2025-08-07 | 2025-08-07 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
32 | Day | 2025-08-07 | 2025-08-07 | Schedule | T2 Synchronised Standard day
32 | Day | 2025-08-08 | 2025-08-08 | Schedule | T2 Synchronised Release day
33 | Week | 2025-08-11 | 2025-08-14 | Schedule | T2 Synchronised Standard day
33 | Day | 2025-08-13 | 2025-08-13 | Special testing | Open ECONSII from 10:00 - 12:00 CET
33 | Day | 2025-08-13 | 2025-08-13 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
33 | Day | 2025-08-14 | 2025-08-14 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
33 | Day | 2025-08-15 | 2025-08-15 | Schedule | T2 Synchronised Release day
34 | Week | 2025-08-18 | 2025-08-21 | Schedule | T2 Synchronised Standard day
34 | Day | 2025-08-20 | 2025-08-20 | Special testing | Open ECONSII from 10:00 - 12:00 CET
34 | Day | 2025-08-20 | 2025-08-20 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
34 | Day | 2025-08-21 | 2025-08-21 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
34 | Day | 2025-08-22 | 2025-08-22 | Schedule | T2 Synchronised Release day
35 | Week | 2025-08-25 | 2025-08-28 | Schedule | T2 Synchronised Standard day
35 | Day | 2025-08-27 | 2025-08-27 | Special testing | Open ECONSII from 10:00 - 12:00 CET
35 | Day | 2025-08-27 | 2025-08-27 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
35 | Day | 2025-08-27 | 2025-08-27 | ORT | T2S ORT "Delay in start of DVP cut-off (DKK)" with impact on T2 | Impact on T2: depending on exact test scenario chosen there will be a delayed closing of CLM and RTGS; EoD and SoD events postponed
35 | Day | 2025-08-28 | 2025-08-28 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
35 | Day | 2025-08-29 | 2025-08-29 | Schedule | T2 Synchronised Release day
36 | Week | 2025-09-01 | 2025-09-04 | Schedule | T2 Synchronised Standard day
36 | Day | 2025-09-03 | 2025-09-03 | Special testing | Open ECONSII from 10:00 - 12:00 CET
36 | Day | 2025-09-03 | 2025-09-03 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
36 | Day | 2025-09-03 | 2025-09-03 | Special testing | BILL invoice for NCBs | Billing period 01/08/-31/08/2025
36 | Day | 2025-09-04 | 2025-09-04 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
36 | Day | 2025-09-05 | 2025-09-05 | Schedule | T2 Synchronised Release day
37 | Week | 2025-09-08 | 2025-09-11 | Schedule | T2 Synchronised Standard day
37 | Day | 2025-09-10 | 2025-09-10 | Special testing | Open ECONSII from 10:00 - 12:00 CET
37 | Day | 2025-09-10 | 2025-09-10 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
37 | Day | 2025-09-11 | 2025-09-11 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
37 | Day | 2025-09-12 | 2025-09-12 | Schedule | T2 Synchronised Release day
38 | Day | 2025-09-15 | 2025-09-15 | Reporting | Service Transition Status Report (STSR) for T2 R2025.NOV in Pre-Production (cut-off and delivery to T2-WG)
38 | Week | 2025-09-15 | 2025-09-18 | Schedule | T2 Synchronised Standard day
38 | Day | 2025-09-16 | 2025-09-16 | Reporting | T2-WG Go / No-go decision to deploy T2 R2025.NOV to Pre-Production | 8 business days before UTEST deployment
38 | Day | 2025-09-17 | 2025-09-17 | Special testing | Open ECONSII from 10:00 - 12:00 CET
38 | Day | 2025-09-17 | 2025-09-17 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
38 | Day | 2025-09-18 | 2025-09-18 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
38 | Day | 2025-09-19 | 2025-09-19 | Schedule | T2 Synchronised Release day
39 | Week | 2025-09-22 | 2025-09-25 | Schedule | T2 Synchronised Standard day
39 | Day | 2025-09-24 | 2025-09-24 | Special testing | Open ECONSII from 10:00 - 12:00 CET
39 | Day | 2025-09-24 | 2025-09-24 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
39 | Day | 2025-09-24 | 2025-09-25 | ORT | T2 ORT "ECONS II two-day test involving T2S"
39 | Day | 2025-09-25 | 2025-09-25 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
39 | Day | 2025-09-26 | 2025-09-26 | Schedule | T2 Synchronised Release day
39 | Day | 2025-09-26 | 2025-09-26 | Release deployment | T2 R2025.NOV deployment to Pre-Production (Packages 1-6) | Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
40 | Day | 2025-09-29 | 2025-09-29 | Release testing | Start of testing of T2 R2025.NOV scope elements in Pre-Production
40 | Week | 2025-09-29 | 2025-10-02 | Schedule | T2 Synchronised Standard day
40 | Week | 2025-09-29 | 2025-10-03 | Release testing | T2 R2025.NOV release testing in Pre-Production
40 | Day | 2025-10-01 | 2025-10-01 | Special testing | Open ECONSII from 10:00 - 12:00 CET
40 | Day | 2025-10-01 | 2025-10-01 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
40 | Day | 2025-10-02 | 2025-10-02 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
40 | Day | 2025-10-02 | 2025-10-02 | Release deployment | T2 R2025.NOV deployment (Package 7) | RDs only / Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
40 | Day | 2025-10-03 | 2025-10-03 | Schedule | T2 Synchronised Release day
40 | Day | 2025-10-03 | 2025-10-03 | Special testing | BILL invoice for NCBs | Billing period 01/09/-30/09/2025
41 | Week | 2025-10-06 | 2025-10-09 | Schedule | T2 Synchronised Standard day
41 | Week | 2025-10-06 | 2025-10-10 | Release testing | T2 R2025.NOV release testing in Pre-Production
41 | Day | 2025-10-08 | 2025-10-08 | Special testing | Open ECONSII from 10:00 - 12:00 CET
41 | Day | 2025-10-08 | 2025-10-08 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
41 | Day | 2025-10-08 | 2025-10-08 | ORT | T2S ORT "Delay in RTGS start (processing without liquidity) (DKK)" with impact on T2 | Impact on T2: a delay in the start of new business day in CLM and RTGS will be simulated
41 | Day | 2025-10-09 | 2025-10-09 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
41 | Day | 2025-10-10 | 2025-10-10 | Schedule | T2 Synchronised Release day
41 | Day | 2025-10-10 | 2025-10-10 | Release deployment | T2 R2025.NOV deployment (Package 8) | RDs only / Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
42 | Week | 2025-10-13 | 2025-10-16 | Schedule | T2 Synchronised Standard day
42 | Week | 2025-10-13 | 2025-10-17 | Release testing | T2 R2025.NOV release testing in Pre-Production
42 | Day | 2025-10-15 | 2025-10-15 | Special testing | Open ECONSII from 10:00 - 12:00 CET
42 | Day | 2025-10-15 | 2025-10-15 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
42 | Day | 2025-10-16 | 2025-10-16 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
42 | Day | 2025-10-16 | 2025-10-16 | ORT | T2 ORT "Suspension of a participant"
42 | Day | 2025-10-17 | 2025-10-17 | Schedule | T2 Synchronised Release day
42 | Day | 2025-10-17 | 2025-10-17 | Release deployment | T2 R2025.NOV deployment (Package 9) | critical RDs only / Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
43 | Week | 2025-10-20 | 2025-10-23 | Schedule | T2 Synchronised Standard day
43 | Week | 2025-10-20 | 2025-10-24 | Release testing | T2 R2025.NOV release testing in Pre-Production
43 | Day | 2025-10-22 | 2025-10-22 | Special testing | Open ECONSII from 10:00 - 12:00 CET
43 | Day | 2025-10-22 | 2025-10-22 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
43 | Day | 2025-10-23 | 2025-10-23 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
43 | Day | 2025-10-24 | 2025-10-24 | Schedule | T2 Synchronised Release day
43 | Day | 2025-10-24 | 2025-10-24 | Release deployment | T2 R2025.NOV deployment (Package 10) | critical RDs only / Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
44 | Week | 2025-10-27 | 2025-10-30 | Schedule | T2 Synchronised Standard day
44 | Week | 2025-10-27 | 2025-10-31 | Release testing | T2 R2025.NOV release testing in Pre-Production
44 | Day | 2025-10-29 | 2025-10-29 | Special testing | Open ECONSII from 10:00 - 12:00 CET
44 | Day | 2025-10-29 | 2025-10-29 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
44 | Day | 2025-10-30 | 2025-10-30 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
44 | Day | 2025-10-31 | 2025-10-31 | Schedule | T2 Synchronised Release day
44 | Day | 2025-10-31 | 2025-10-31 | Release deployment | T2 R2025.NOV deployment (Package 11) | critical RDs only / Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
45 | Week | 2025-11-03 | 2025-11-05 | Release testing | T2 R2025.NOV release testing in Pre-Production
45 | Week | 2025-11-03 | 2025-11-06 | Schedule | T2 Synchronised Standard day
45 | Day | 2025-11-05 | 2025-11-05 | Special testing | Open ECONSII from 10:00 - 12:00 CET
45 | Day | 2025-11-05 | 2025-11-05 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
45 | Day | 2025-11-05 | 2025-11-05 | Special testing | BILL invoice for NCBs | Billing period 01/10/-31/10/2025
45 | Day | 2025-11-05 | 2025-11-05 | Release testing | End of testing of T2 R2025.NOV scope elements in Pre-Production
45 | Day | 2025-11-06 | 2025-11-06 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
45 | Day | 2025-11-07 | 2025-11-07 | Schedule | T2 Synchronised Release day
45 | Day | 2025-11-07 | 2025-11-07 | Release deployment | T2 R2025.NOV deployment (Package 12) | critical RDs only / Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
46 | Week | 2025-11-10 | 2025-11-13 | Schedule | T2 Synchronised Standard day
46 | Day | 2025-11-12 | 2025-11-12 | Special testing | Open ECONSII from 10:00 - 12:00 CET
46 | Day | 2025-11-12 | 2025-11-12 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
46 | Day | 2025-11-13 | 2025-11-13 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
46 | Day | 2025-11-14 | 2025-11-14 | Schedule | T2 Synchronised Release day
47 | Week | 2025-11-17 | 2025-11-20 | Schedule | T2 Synchronised Standard day
47 | Day | 2025-11-19 | 2025-11-19 | Special testing | Open ECONSII from 10:00 - 12:00 CET
47 | Day | 2025-11-19 | 2025-11-19 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
47 | Day | 2025-11-20 | 2025-11-20 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
47 | Day | 2025-11-21 | 2025-11-21 | Schedule | T2 Synchronised Release day
48 | Week | 2025-11-24 | 2025-11-27 | Schedule | T2 Synchronised Standard day
48 | Day | 2025-11-26 | 2025-11-26 | Special testing | Open ECONSII from 10:00 - 12:00 CET
48 | Day | 2025-11-26 | 2025-11-26 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
48 | Day | 2025-11-27 | 2025-11-27 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
48 | Day | 2025-11-28 | 2025-11-28 | Schedule | T2 Synchronised Release day
49 | Week | 2025-12-01 | 2025-12-04 | Schedule | T2 Synchronised Standard day
49 | Day | 2025-12-03 | 2025-12-03 | Special testing | Open ECONSII from 10:00 - 12:00 CET
49 | Day | 2025-12-03 | 2025-12-03 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
49 | Day | 2025-12-03 | 2025-12-03 | Special testing | BILL invoice for NCBs | Billing period 01/11/-30/11/2025
49 | Day | 2025-12-04 | 2025-12-04 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
49 | Day | 2025-12-05 | 2025-12-05 | Schedule | T2 Synchronised Release day
50 | Week | 2025-12-08 | 2025-12-11 | Schedule | T2 Synchronised Standard day
50 | Day | 2025-12-10 | 2025-12-10 | Special testing | Open ECONSII from 10:00 - 12:00 CET
50 | Day | 2025-12-10 | 2025-12-10 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
50 | Day | 2025-12-10 | 2025-12-10 | ORT | T2S ORT "RAD Tests (Inter regional failover with loss of data)" with impact on T2 | Impact on T2: a snapshot of the system will be taken during the evening before the test and reloaded the day after in the morning. All the updates performed in the system (UTEST), included CoCo, will be lost.
50 | Day | 2025-12-11 | 2025-12-11 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
50 | Day | 2025-12-12 | 2025-12-12 | Schedule | T2 Synchronised Release day
51 | Week | 2025-12-15 | 2025-12-18 | Schedule | T2 Synchronised Standard day
51 | Day | 2025-12-17 | 2025-12-17 | Special testing | Open ECONSII from 10:00 - 12:00 CET
51 | Day | 2025-12-17 | 2025-12-17 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
51 | Day | 2025-12-18 | 2025-12-18 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
51 | Day | 2025-12-19 | 2025-12-19 | Schedule | T2 Synchronised Release day
52 | Day | 2025-12-22 | 2025-12-23 | Schedule | T2 Synchronised Standard day
52 | Day | 2025-12-24 | 2025-12-24 | Schedule | T2 closing day | Christmas Eve
52 | Day | 2025-12-25 | 2025-12-25 | Schedule | T2 closing day | Christmas Day
52 | Day | 2025-12-26 | 2025-12-26 | Schedule | T2 closing day | Boxing Day
53 | Day | 2025-12-29 | 2025-12-30 | Schedule | T2 Synchronised Standard day
53 | Day | 2025-12-30 | 2025-12-30 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
53 | Day | 2025-12-31 | 2025-12-31 | Schedule | T2 closing day | New Year's Eve
1 | Day | 2026-01-01 | 2026-01-01 | Schedule | T2 Synchronised Standard day
1 | Day | 2026-01-02 | 2026-01-02 | Schedule | T2 Synchronised Release day
2 | Day | 2026-01-06 | 2026-01-06 | Special testing | BILL invoice for NCBs | Billing period 01/12/-31/12/2025
11 | Day | 2026-03-13 | 2026-03-13 | Reporting | T2-WG Go / No-go decision to deploy T2 R2026.JUN to Pre-Production
13 | Day | 2026-03-27 | 2026-03-27 | Release deployment | T2 R2026.JUN deployment to Pre-Production (Packages 1-8)
16 | Day | 2026-04-17 | 2026-04-17 | Release deployment | T2 R2026.JUN deployment (Package 9) | Any release scope elements & RD
17 | Day | 2026-04-24 | 2026-04-24 | Release deployment | T2 R2026.JUN deployment (Package 10) | RD only
18 | Day | 2026-04-30 | 2026-04-30 | Release deployment | T2 R2026.JUN deployment (Package 11) | RD only
19 | Day | 2026-05-07 | 2026-05-07 | Release deployment | T2 R2026.JUN deployment (Package 12) | RD only
20 | Day | 2026-05-13 | 2026-05-13 | Release deployment | T2 R2026.JUN deployment (Package 13) | RD only
21 | Day | 2026-05-22 | 2026-05-22 | Release deployment | T2 R2026.JUN deployment (Package 14) | critical RD only
22 | Day | 2026-05-29 | 2026-05-29 | Release deployment | T2 R2026.JUN deployment (Package 15) | critical RD only
23 | Day | 2026-06-05 | 2026-06-05 | Release deployment | T2 R2026.JUN deployment (Package 16) | critical RD only
38 | Day | 2026-09-15 | 2026-09-15 | Reporting | T2-WG Go / No-go decision to deploy T2 R2026.NOV to Pre-Production
39 | Day | 2026-09-25 | 2026-09-25 | Release deployment | T2 R2026.NOV deployment to Pre-Production (Packages 1-6)
40 | Day | 2026-10-02 | 2026-10-02 | Release deployment | T2 R2026.NOV deployment (Package 7) | RD only
41 | Day | 2026-10-09 | 2026-10-09 | Release deployment | T2 R2026.NOV deployment (Package 8) | RD only
42 | Day | 2026-10-16 | 2026-10-16 | Release deployment | T2 R2026.NOV deployment (Package 9) | critical RD only
43 | Day | 2026-10-23 | 2026-10-23 | Release deployment | T2 R2026.NOV deployment (Package 10) | critical RD only
44 | Day | 2026-10-30 | 2026-10-30 | Release deployment | T2 R2026.NOV deployment (Package 11) | critical RD only
45 | Day | 2026-11-06 | 2026-11-06 | Release deployment | T2 R2026.NOV deployment (Package 12) | critical RD only
Formulas:
Week number = WEEKNUM([Start Date])